## Product Backlog
| Item # | Description | Est Duration | By | Sprint #
High
| 1 | Understand how the game is played | 6 | Tanishq, Max, Elizabeth, Justin | 1
| 2 | Make UML Diagrams | 4 | Tanishq | 1
1
Medium
| 3 | Document Using JavaDoc Standards | 6 | Max, Elizabeth, Justin | 1
| - | Create Team Nations | - | - | 1
| 4 | Create Tanishq's Nation | 2 | Tanishq | 1
| 5 | Create Max's Nation | 2 | Max | 1
| 6 | Create Elizabeth's Nation | 2 | Elizabeth | 1
| 7 | Create Justin's Nation | 2 | Justin | 1
Low
| 8 | Add Player Type Healer | 4 | Justin | 1