## Agile Sprint Backlog
AGILE SPRINT #1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | 2021-02-23 | 2021-02-25 | 2021-03-02 | 2021-03-04 | 2021-03-05 | SPRINT REVIEW
User Story #1
Make UML Chart | 4 | Tanishq | Done | 4 Hours | 1 | 2 | 0 | 0 | 0
Add Player Type Healer | 2 | Justin | Done | 2 Hours | 1 | 0 | 0 | 0 | 0
Document using JavaDoc Standards | 6 | Max/Elizabeth/Justin | TBD | 6 Hours | 0 | 1 | 1 | 2 | 1
Create a Random Number Generator on a Spreadsheet | 1 | Justin | Done | 1 Hours | 0 | 0 | 1 | 0 | 0
User Story #2
Create Max's Nation | 2 | Max | Done | 2 Hours | 0 | 1 | 0 | 0 | 0
Create Elizabeth's Nation | 2 | Elizabeth | Done | 2 Hours | 1 | 0 | 0 | 0 | 0
Create Justin's Nation | 2 | Justin | Done | 2 Hours | 0 | 0 | 1 | 0 | 0
Create Tanishq's Nation | 2 | Tanishq | Done | 2 Hours | 0 | 1 | 0 | 0 | 0
User Story #3
Make Notecards | 1 | Max/Justin/Elizabeth/Tanishq | Done | 1 Hour | 0 | 0 | 0 | 0 | 1
Learn Rules of Game | 6 | Everyone | Done | 5 Hours | 1 | 1 | 2 | 1 | 1
TOTAL |  |  |  | 28 | 7 | 3 | 5 | 3 | 3
|  |  |  | 28 | 21 | 18 | 13 | 10 | 7

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0